## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Project Setup & Architecture Design (FastAPI + Airflow + Docker) | MUST HAVE | Docker, Python 3.11 | Team | 3- Completed
S1 | S1 | US-002 | Database Schema & PostgreSQL Setup with Alembic Migrations | MUST HAVE | PostgreSQL 15, SQLAlchemy | Team | 3- Completed
S2 | S2 | US-003 | CSV Extractor Module (plugin-based extractor with incremental support) | MUST HAVE | Pandas 2.2, PyArrow | Team | 3- Completed
S2 | S2 | US-004 | SQL Extractor Module (incremental extraction with watermark support) | MUST HAVE | SQLAlchemy 2.0 | Team | 3- Completed
S3 | S3 | US-005 | REST API Extractor Module (authentication, pagination, retry logic) | MUST HAVE | httpx, Pydantic Settings | Team | 3- Completed
S3 | S3 | US-006 | Universal File Parser (CSV/Excel/JSON/TXT/PDF/DOCX ingestion) | MUST HAVE | pdfplumber, python-docx, openpyxl | Team | 3- Completed
S4 | S4 | US-007 | Transformation Engine (10-rule engine: dedup, null fill, type coercion, normalisation) | MUST HAVE | Pandas, NumPy | Team | 3- Completed
S4 | S4 | US-008 | 5-Dimension Data Quality Scorer (0–100 score, grade A–F, radar chart) | MUST HAVE | Plotly 5.18 | Team | 3- Completed
S5 | S5 | US-009 | PostgreSQL / CSV / Parquet Loader Module with upsert and partitioning | MUST HAVE | PyArrow, SQLAlchemy | Team | 3- Completed
S5 | S5 | US-010 | Pipeline Service (lifecycle management, scheduling, status tracking) | MUST HAVE | FastAPI, asyncio | Team | 3- Completed
S6 | S6 | US-011 | Apache Airflow DAG: Customer Data Pipeline (full production DAG) | MUST HAVE | Airflow 2.8, Celery, Redis | Team | 3- Completed
S6 | S6 | US-012 | Dynamic DAG Generator (YAML → DAG factory, zero-code pipeline creation) | SHOULD HAVE | Airflow, PyYAML | Team | 3- Completed
S7 | S7 | US-013 | FastAPI REST Backend (11 endpoints: pipelines, datasources, metrics, health) | MUST HAVE | FastAPI, Uvicorn | Team | 3- Completed
S7 | S7 | US-014 | Email & Slack Alerting Service (SLA breach, pipeline failure notifications) | SHOULD HAVE | SMTP, Slack API | Team | 2- In Progress
S8 | S8 | US-015 | Streamlit 7-Page Enterprise Dashboard (dark mode, KPI cards, live charts) | MUST HAVE | Streamlit 1.31, Plotly | Team | 2- In Progress
S8 | S8 | US-016 | Monitoring & Job Tracker (SLA reports, stalled pipeline detection) | SHOULD HAVE | Structlog (JSON) | Team | 2- In Progress
S9 | S9 | US-017 | Unit & Integration Testing Suite (66 unit + 9 integration tests, pytest) | MUST HAVE | pytest 8.0, coverage | Team | 2- In Progress
S9 | S9 | US-018 | Docker Compose Infrastructure (8 services: API, Airflow, Dashboard, DB, Redis) | MUST HAVE | Docker Compose | Team | 1- Not Started
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
SPRINT 1 BACKLOG
US-001 | 1 | Project Setup & Architecture Design | 2026-01-05 | 2026-01-07 | Team | Design | 3- Completed | 4 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | 2 | PostgreSQL Schema & Alembic Migrations Setup | 2026-01-08 | 2026-01-10 | Team | Build | 3- Completed | 5 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | 3 | CSV Extractor Plugin with Incremental Support | 2026-01-13 | 2026-01-16 | Team | Coding | 3- Completed | 6 | 2 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | 4 | SQL Extractor Module with Watermark Support | 2026-01-17 | 2026-01-21 | Team | Coding | 3- Completed | 8 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 2 BACKLOG
US-005 | 1900-01-04 | REST API Extractor (auth, pagination, retry logic) | 2026-01-26 | 2026-01-29 | Team | Coding | 3- Completed | 8 | 3 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | 1900-01-05 | Universal File Parser (CSV/Excel/JSON/TXT/PDF/DOCX) | 2026-01-30 | 2026-02-05 | Team | Coding | 3- Completed | 10 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-007 | 1900-01-06 | Transformation Engine (10-rule engine) | 2026-02-06 | 2026-02-11 | Team | Coding | 3- Completed | 12 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 3 BACKLOG
US-008 | 1900-01-07 | 5-Dimension Data Quality Scorer (0–100, grade A–F) | 2026-02-16 | 2026-02-20 | Team | Build | 3- Completed | 8 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-009 | 1900-01-08 | PostgreSQL/CSV/Parquet Loader with Upsert & Partitioning | 2026-02-23 | 2026-02-27 | Team | Coding | 3- Completed | 10 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-010 | 1900-01-09 | Pipeline Service (lifecycle management, scheduling, status tracking) | 2026-03-02 | 2026-03-06 | Team | Coding | 3- Completed | 12 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 4 BACKLOG
US-011 | 1900-01-10 | Airflow Customer Data Pipeline DAG (full production DAG) | 2026-03-09 | 2026-03-13 | Team | Build | 3- Completed | 10 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-012 | 1900-01-11 | Dynamic DAG Generator (YAML → DAG factory) | 2026-03-16 | 2026-03-19 | Team | Build | 3- Completed | 8 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-013 | 1900-01-12 | FastAPI REST Backend (11 endpoints) | 2026-03-20 | 2026-03-24 | Team | Coding | 3- Completed | 10 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 5 BACKLOG
US-014 | 14 | Email & Slack Alerting Service | 2026-03-30 | 2026-04-02 | Team | Integration Test | 2- In Progress | 6 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-015 | 15 | Streamlit 7-Page Enterprise Dashboard (dark mode) | 2026-04-03 | 2026-04-08 | Team | Build | 2- In Progress | 12 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-016 | 16 | Monitoring & Job Tracker (SLA reports, stalled detection) | 2026-04-09 | 2026-04-12 | Team | System Test | 1- Not Started | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-017 | 17 | Unit & Integration Testing Suite (75 tests) | 2026-04-13 | 2026-04-16 | Team | System Test | 1- Not Started | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-018 | 18 | Docker Compose Infrastructure (8 services) | 2026-04-17 | 2026-04-19 | Team | Others | 1- Not Started | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Unclear project scope for ETL platform modules | Conducted architecture review session; defined 8 core modules and Docker service layout
Sprint 1 | Day 3 | Team unfamiliar with Alembic migration workflows | Ran internal knowledge-sharing session on Alembic and SQLAlchemy 2.0 async patterns
Sprint 2 | Day 5 | CSV extractor failing on large files due to memory issues | Implemented chunked reading with PyArrow; resolved within same day
Sprint 2 | Day 8 | API extractor pagination logic breaking on non-standard APIs | Reviewed API docs; added configurable pagination strategy per source type
Sprint 3 | Day 11 | Universal file parser not handling corrupted PDF files gracefully | Added try-catch with pdfplumber fallback; implemented error logging via Structlog
Sprint 3 | Day 13 | Transformation rule ordering causing data loss in edge cases | Fixed rule sequencing; added 12 additional unit tests to cover edge cases
Sprint 4 | Day 16 | Airflow DAG scheduling conflicts between customer and sales pipelines | Set staggered start times; verified with dynamic DAG generator YAML configs
Sprint 4 | Day 19 | FastAPI async endpoints timing out on large dataset loads | Switched to background tasks with Celery; added timeout configuration in .env
Sprint 5 | Day 22 | Streamlit dashboard slow to render with 10+ live Plotly charts | Implemented caching with @st.cache_data; reduced dashboard load time by 60%
Sprint 5 | Day 24 | Docker Compose memory issues running all 8 services simultaneously | Tuned resource limits in docker-compose.yml; documented minimum spec requirements

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-01-05 | 2026-01-21 | Team | Documenting architecture decisions before coding | Jumping into implementation without a design doc | Daily async standups via Slack | Created architecture diagram and module responsibility matrix before Sprint 2
2 | Sprint 2 | 2026-01-26 | 2026-02-11 | Team | Writing unit tests alongside feature development | Skipping edge case testing under time pressure | Pair code review on all extractor modules | Added 20 unit tests for extractor edge cases; caught 3 critical bugs early
3 | Sprint 3 | 2026-02-16 | 2026-03-06 | Team | Adding structured logging from the start of each module | Hardcoding config values in code | Using Pydantic Settings for all environment config | Migrated all hardcoded values to .env.example; Structlog JSON logging adopted fully
4 | Sprint 4 | 2026-03-09 | 2026-03-24 | Team | Validating Airflow DAGs in local dev before merging | Merging untested DAG changes to main | YAML-driven pipeline config pattern (zero-code) | All 2 pipeline configs validated end-to-end; DAG generator tested with 4 YAML configs
5 | Sprint 5 | 2026-03-30 | 2026-04-19 | Team | Performance profiling before demo deployments | Ignoring Docker resource limits until deployment | Agile retrospection and sprint planning cadence | Dashboard load time cut by 60%; Docker Compose resource tuning completed
6
7